## Agile Project Plan - SAMPLE
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  |  |  | PROJECT DELIVERABLE | Base functionality to allow user to utulize the system
| Product Release | Alex B. | 2022-09-02 | 2022-10-10 |  |  |  | SCOPE STATEMENT
AT RISK | TASK NAME | USER STORY | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. | 10 | 2022-09-03 | 2022-09-07 | 4 | Done
| Feature 1 | US01 | Frank C. | 4 | 2022-09-03 | 2022-09-07 | 4 | Done |  | USE THIS AS A BASELINE EXAMPLE WHEN PLANNING YOUR OWN PROJECT OUT- - Assign smaller tasks based on the sprint length that are manageable - Ensure that the Scrum master/Project manager is continually updating this sheet during Sprint retrospective meetings/planning sessions/Standup meetings
| Task 1 | Design interface | Frank C. | 2
| Task 2 | Develop interface | Frank C. | 1
| Task 3 | Test interface | Frank C. | 1
| Feature 2 | US02 | Jacob S. | 3 | 2022-09-05 | 2022-09-07 | 2 | Done
| Task 1 | Develop Login Functionality | Jacob S. | 1
| Task 2 | Password strength checker | Jacob S. | 1
| Task 3 | Confirm password functionality | Jacob S. | 1
| Feature 3 | US18 | Jacob S. | 3 | 2022-09-09 | 2022-09-13 | 4 | Not Done
| Task 1 |  | Jacob S. | 1
| Task 2 |  | Jacob S. | 1
| Task 3 |  | Jacob S. | 1
| Sprint Testing |  | Alex B.
| Sprint 2 |  | Jacob S. | 10 | 2022-09-16 | 2022-09-24 | 8 | Not Done
| Feature 4 | US08 | Alex B. | 2 | 2022-09-16 | 2022-09-17 | 1 | Not Done
| Task 1 |  | Alex B. | 1
| Task 2 |  | Alex B. | 1
| Feature 5 | US04 | Frank C. | 3 | 2022-09-17 | 2022-09-21 | 4 | Not Started
| Task 1 |  | Frank C. | 3
| Feature 6 | US12 | Shari W. | 5 | 2022-09-22 | 2022-09-24 | 2 | Not Started
| Task 1 |  | Shari W. | 2
| Task 2 |  | Shari W. | 1
| Task 3 |  | Shari W. | 2
| Sprint Testing |  | Jacob S.
| Sprint 3 |  | Shari W. | 10 | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 | US06 | Alex B. | 4 | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Task 1 |  | Alex B. | 4
| Feature 8 | US07 | Kennedy K. | 4 | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Task 1 |  | Kennedy K. | 4
| Feature 9 | US14 | Jacob S. | 2 | 2022-10-02 | 2022-10-05 | 3 | Not Started
| Task 1 |  | Jacob S. | 2
| Sprint Testing |  | Shari W.

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  |  |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | USER STORY | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint Testing
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint Testing
Sprint 3
Feature 7
Feature 8
Feature 9
Sprint Testing